## 3-Year Gantt Chart Example
PROJECT TITLE
START DATE
2023-12-15
[5 empty] | YEAR ONE | [11 empty] | YEAR TWO | [11 empty] | YEAR THREE | [11 empty] | DO NOT ALTER CELL BELOW
[5 empty] | Y1Q1 |  |  | Y1Q2 |  |  | Y1Q3 |  |  | Y1Q4 |  |  | Y2Q1 |  |  | Y2Q2 |  |  | Y2Q3 |  |  | Y2Q4 |  |  | Y3Q1 |  |  | Y3Q2 |  |  | Y3Q3 |  |  | Y3Q4
TASK TITLES | TASK OWNER(S) | START DATE | END DATE | # of Days | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01
Finalize protocol, apply for grant | PI | 2023-12-02 | 2024-05-20 | 121 | bar: 2023-12-01 to 2024-05-01
Training of PI Collaborators | RP | 2023-12-02 | 2024-04-15 | 96 | bar: 2023-12-01 to 2024-04-01
Obtain IRB approval | PI | 2023-12-02 | 2024-02-15 | 54 | bar: 2023-12-01 to 2024-02-01
Acquire needed materials | PI | 2023-12-01 | 2024-02-15 | 55 | bar: 2023-12-01 to 2024-02-01
Seek out additional avenues for recruitment | PI, GRA | 2024-02-01 | 2024-05-01 | 65 | bar: 2024-02-01 to 2024-05-01
Begin recruitment | PI, GRA | 2024-03-01 | 2024-08-15 | 120 | bar: 2024-03-01 to 2024-08-01
Schedule On-Site Lab Visits | PI, GRA | 2024-03-01 | 2024-08-01 | 110 | bar: 2024-03-01 to 2024-08-01
Begin evaluation of outcome data | PI, DM | 2024-09-01 | 2024-10-01 | 22 | bar: 2024-09-01 to 2024-10-01
Preliminary Report | PI, RP, DM | 2024-11-01 | 2024-11-30 | 21 | bar: 2024-11-01
Complete evaluation report | PI, RP, DM | 2024-11-01 | 2024-12-15 | 31 | bar: 2024-11-01 to 2024-12-01
Use pilot data to seek NIDCD grant | PI, RP, DM | 2024-11-01 | 2024-12-15 | 31 | bar: 2024-11-01 to 2024-12-01

## BLANK - 3-Year Gantt Chart
ENTER PROJECT TITLE
START DATE
2024-03-01 | <-- Enter initial Start Date to populate Timeline dates.
Enter each Task Start and End Date per Project, below. Project Dates and # of Days will calculate automatically. |  |  |  |  | YEAR ONE | [11 empty] | YEAR TWO | [11 empty] | YEAR THREE | [11 empty] | DO NOT ALTER CELL BELOW
[5 empty] | Y1Q1 |  |  | Y1Q2 |  |  | Y1Q3 |  |  | Y1Q4 |  |  | Y2Q1 |  |  | Y2Q2 |  |  | Y2Q3 |  |  | Y2Q4 |  |  | Y3Q1 |  |  | Y3Q2 |  |  | Y3Q3 |  |  | Y3Q4
TASK TITLES | TASK OWNER(S) | START DATE | END DATE | # of Days | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01
Task 1 |  |  |  | 0
Task 2 |  |  |  | 0
Task 3 |  |  |  | 0
Task 4 |  |  |  | 0
Task 5 |  |  |  | 0
Task 6 |  |  |  | 0
Task 7 |  |  |  | 0
Task 8 |  |  |  | 0
Task 9 |  |  |  | 0
Task 10 |  |  |  | 0
Task 11 |  |  |  | 0
Task 12 |  |  |  | 0
Task 13 |  |  |  | 0
Task 14 |  |  |  | 0
Task 15 |  |  |  | 0
Task 16 |  |  |  | 0
Task 17 |  |  |  | 0
Task 18 |  |  |  | 0
Task 19 |  |  |  | 0
Task 20 |  |  |  | 0